## Contents
Department of Health annual report 2021-22 – machine readable dataset:
Capital projects reaching practical and financial completion
Contents
Capital projects reaching practical completion during the financial year ended 30 June 2022
Capital projects reaching financial completion during the financial year ended 30 June 2022
Accessibility
To receive this data in another format, email corporate reporting
<corporate.reporting@health.vic.gov.au>.
Copyright
With the exception of any images, photographs or branding (including, but not limited to the Victorian Coat of Arms, the Victorian Government logo or the Department of Health logo), this work, Department of Health Annual Report 2021–22, is licensed under a Creative Commons Attribution 4.0 licence.
The terms and conditions of this licence, including disclaimer of warranties and limitation of liability are available at Creative Commons Attribution 4.0 International <https://creativecommons.org/licenses/by/4.0/legalcode>.
You are free to reuse the work under that licence, on the condition that you credit the State of Victoria, Australia (Department of Health) as the author and/or owner of the work, indicate if any changes have been made to the work and comply with the other licence terms.
In this document, ‘Aboriginal’ refers to both Aboriginal and Torres Strait Islander people. ‘Indigenous’ or ’Koori/Koorie’ is retained when part of the title of a report, program or quotation.
ISSN 2653-1852 (online) (DH 2205209)
Available at Department of Health annual report <https://www.health.vic.gov.au/department-of-health-annual-report>

## Capital projects prac. compl.
Capital projects reaching practical completion during the financial year ended 30 June 2022
Project name | Original completion date | Latest approved completion date | Practical completion date | Reason for variance in completion dates | Original approved TEI budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost ($M) | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
Monash Medical Centre – infrastructure upgrades (Clayton) | 2022-06-01 | 2023-06-01 | 2022-05-01 | Updated to reflect project delivery and change in scope | 63.2 | 76.3 | 71.694 | 4.606 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Northern Hospital inpatient expansion – Stage 2 (Epping) | 2022-06-01 | 2022-12-01 | 2021-08-01 | Updated to reflect project delivery and change in scope | 162.672 | 162.672 | 158.535 | 4.137 | Balance of funding is required for financial closeout of the project, expected in the next financial year.
Regional Drug Residential Rehabilitation Services (regional various) | 2021-06-01 | 2023-06-01 | 2021-11-01 | Updated to reflect project delivery and change in scope | 40.6 | 52.1 | 48.344 | 3.756 | All sites have been handed over as part of Separable Portion 1. Final activities progressing on schedule, with balance of funding required for financial closeout of the project, expected in the next financial year.
Youth Prevention and Recovery Care (PARC) Service (metropolitan Melbourne) | 2021-12-01 | 2023-12-01 | 2021-12-01 | Updated to reflect project delivery and change in scope | 11.9 | 12.9 | 11.403 | 1.497 | Balance of funding is required for financial closeout of the project, expected in the next financial year.

## Capital projects fin. compl.
Capital projects reaching financial completion during the financial year ended 30 June 2022
Project name | Practical completion date | Financial completion date | Original approved TEI budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost ($M) | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
Modernisation of metro public sector residential aged care (Kew) | 2020-08-01 | 2021-12-01 | 57.57 | 57.57 | 57.57 | 0 | N/A
Mental health and alcohol and other drugs facilities renewal 2017–18 (statewide) | 2022-06-01 | 2022-06-01 | 10 | 10 | 10 | 0 | N/A
Western Health urgent infrastructure works (Footscray and Sunshine) | 2021-06-01 | 2022-06-01 | 61.335 | 61.335 | 61.335 | 0 | N/A
World-Class Care for Wangaratta Patients (Wangaratta) | 2022-06-01 | 2022-06-01 | 7.506 | 7.506 | 7.506 | 0 | N/A