## Contents
Department of Health annual report 2020-21 – machine readable dataset:
Capital projects reaching practical and financial completion
Contents
Capital projects reaching practical completion during the financial year ended 30 June 2021
Capital projects reaching financial completion during the financial year ended 30 June 2021
Accessibility
To receive this data in another format, email corporate reporting
<corporate.reporting@health.vic.gov.au>.
Copyright
With the exception of any images, photographs or branding (including, but not limited to the Victorian Coat of Arms, the Victorian Government logo or the Department of Health logo), this work, Department of Health annual report 2020–21, is licensed under a Creative Commons Attribution 4.0 licence.
The terms and conditions of this licence, including disclaimer of warranties and limitation of liability are available at Creative Commons Attribution 4.0 International <https://creativecommons.org/licenses/by/4.0/legalcode>.
You are free to reuse the work under that licence, on the condition that you credit the State of Victoria, Australia (Department of Health) as the author and/or owner of the work, indicate if any changes have been made to the work and comply with the other licence terms.
In this document, ‘Aboriginal’ refers to both Aboriginal and Torres Strait Islander people. ‘Indigenous’ or ’Koori/Koorie’ is retained when part of the title of a report, program or quotation.
ISSN 2653-1852 (online)
Available at Department of Health annual report <https://www.health.vic.gov.au/department-of-health-annual-report>

## Capital projects - pract. compl
Capital projects reaching practical completion during the financial year ended 30 June 2021
Project name | Original completion date | Latest approved completion date | Practical completion date | Reason for variance in completion dates | Original approved TEI budget ($M) | Latest approved TEI budget ($M) | Actual TEI cost | Variation between actual cost and latest approved TEI budget ($M) | Reason for variance from latest approved TEI budget
Modernisation of metro public sector residential aged care (Kew) | 2019-06-01 | 2021-12-01 | 2020-08-01 |  | 57.57 | 57.57 | 56.634 | -0.936 | Balance of funding is required for financial closeout of the project, noting the project has entered Defects Liability Period.
Royal Melbourne Hospital – critical infrastructure works | 2019-12-01 | 2022-06-01 | 2020-12-01 |  | 40 | 40 | 37.875 | -2.125 | Balance of funding is required for financial closeout of the project. Project concluded the Defects Liability Period in December 2020 and financial closure is in progress.

## Capital projects fin. compl.
Capital projects reaching financial completion during the financial year ended 30 June 2021 - cont.
Project name | Practical completion date | Financial completion date | Original approved | Latest approved TEI budget | Actual TEI cost | Variation between | Reason for variance from latest approved TEI budget
Casey Hospital Expansion | 2020-04-01 | 2021-06-01 | 1900-01-01 09:36 | 139.78 | 124.562 | -15.218 | Original TEI was for planning only. Latest approved TEI includes $5 million contribution from Monash University for accommodation space. Final expenditure excludes financing costs.
Austin Health Critical infrastructure | 2019-06-01 | 2021-06-01 | 1900-02-08 19:12 | 62.816 | 66.409 | 3.593 | Variance impacted by decrease in TEI by $7.8 million with amount reallocated towards the new Austin Central Sterile Services Department (Heidelberg). Actual TEI cost reflects actual project expenditure.
Barwon Health – North | 2019-07-01 | 2021-06-01 | 1900-01-27 01:55 | 33.08 | 30.573 | -2.507 | TEI increase to reflect additional funding for site location. Defects Liability period concluded July 2020. Actual TEI cost reflects actual project expenditure.
Clinical Technology Refresh 2019–20 (statewide) | 2020-06-01 | 2021-06-01 | 1900-01-12 | 13 | 13
Forensic mental health implementation plan – priority service reforms (Footscray) | 2020-06-01 | 2021-06-01 | 1900-01-02 21:36 | 5.942 | 5.877 | -0.65 | TEI was increased to include revised project scope.
Grampians Prevention and Recovery Care (PARC) Services (Ballarat) | 2020-04-01 | 2021-06-01 | 1900-01-05 | 6 | 5.828 | -0.172
Supporting Demand for Ambulance Services | 2019-06-01 | 2021-06-01 | 1900-01-02 08:17 | 3.345 | 3.345
The Joan Kirner Women’s and Children’s Hospital | 2020-06-01 | 2021-06-01 | 1900-07-18 | 200 | 200